## Sheet1
PROJECT CHARTER
Project Title : Tick-Tac-Toe |  |  | Project Manager : Dr.Case
Project Start Date :5/26/21 |  | Project Sponsor : Northwest Missouri State University
Business Need
Generates money from ads and user data
Project Scope |  |  |  | Deliverables
Create a online game to acces from anywhere |  |  | There will be a simple square game board divided into nine tiles or grid spaces with instructions.
Risks and Issues |  |  | Assumptions/Dependencies
User data may leads to privacy issues |  |  | Need to check the terms and conditions while sinning up
Milestones Schedule
Milestone |  |  | Target completion Date |  | Actual Date
Milestone 1 - Gather All requirements for project |  |  | 2021-06-21 |  | 2021-06-22
Milestone 2- Deploy the first version |  |  | 2021-08-08 |  | 2021-08-10
Milestone 3 - Deploy the final version |  |  | 2021-08-29 |  | 2021-08-31
Project Team |  |  | Approval/Review Committee
Product Owner | Sri Vasavi Vipparla |  | Sponsor |  | NMSU
Scrum Master | Manoj Nuvvala |  | Business Unit Head |  | Terry Immel
Developer | Abhilash Ramavaram |  | Business Divison Head |  | Dr. Bandi Ajay
Designer | Madhu Babu Arla |  | Finance Manager |  | Melissa Cook